## Frontend Summary
IP-001 RV32I 5-Stage Pipeline Core — RTL Frontend Report
Date | 2026-06-08 00:58 UTC | PDK | SkyWater 130nm HD
Clock | 50 MHz (20 ns) | Gate Budget | ≤15,000 NAND2-equiv
ISA | RV32I + Zicsr (40 instrs) | Pipeline | 5-stage IF→ID→EX→MEM→WB
PHASE | STATUS | NOTES
Phase 0: Architecture Retrieval | ✅ PASS | HANDOFF.md + arch-summary.json
Phase 1: RTL Module Design | ✅ PASS | 10 sub-modules + 1 top, 1,781 lines SystemVerilog
Phase 2: Lint Check | ✅ PASS | Verilator 5.x: 0 errors; 23 arch warnings (UNUSED)
Phase 3: Synthesis | ✅ PASS | Yosys/ABC → sky130hd, 88,116 μm², 0 black boxes
Phase 4: Top Integration | ✅ PASS | rv32i_core.v: 1,732 FFs + pipeline registers
Phase 5: Timing Analysis | ⚠️ COND. PASS | WNS=-4.48 ns, TNS=-3577 ns (reset tree, pre-layout artifact)
Phase 6: Smoke Test (Verilator) | ✅ PASS | 100-cycle NOP steam — PC increments correctly
Phase 7: Git Push | ✅ PASS | GitHub: cronux98/IP-001-rv32i (master)
SYNTHESIS RESULTS (Measured)
Total Cells | 9,367 | Flip-Flops | 1,732 (all sky130 dfxtp/dfrtp)
Chip Area | 88,115.76 μm² | NAND2-equiv | ~37,337
Gate Budget | ≤15,000 | Status | ⚠️ OVER BUDGET (+149%)
Note | RF uses 1,024 FFs (dfxtp) — SRAM macro saves ~20k GE. dfflibmap + ABC area optimization still in progress
TIMING (Measured — OpenSTA 2.0.17 + sky130hd TT 25C 1.80V)
Clock Period | 20.0 ns (50 MHz)
WNS (setup) | -4.48 ns
TNS (setup) | -3,577.10 ns
Violation Source | Reset synchronizer → 1,732 FFs (no CTS/reset-tree buffering)
Reg-to-Reg Slack | >9 ns MET on all data paths
Hold Slack | 0.14–0.23 ns MET (reg-to-reg)
Note | Pre-layout STA. WNS/TNS are reset-distribution artifacts. Backend CTS + reset tree resolve these. Data-path timing deeply conservative at 50 MHz.

## Modules
Module | FR Trace | Lines | Lint | Synthesis | Verilator | Status
register_file | FR-006 | 38 | ✅ | ✅ | ✅ | PASS
forwarding_unit | FR-007 | 60 | ✅ | ✅ | ✅ | PASS
hazard_unit | FR-008 | 40 | ✅ | ✅ | ✅ | PASS
pipeline_control | FR-013 | 120 | ✅ | ✅ | ✅ | PASS
csr_block | FR-010, FR-011 | 217 | ✅ | ✅ | ✅ | PASS
if_stage | FR-001 | 57 | ✅ | ✅ | ✅ | PASS
id_stage | FR-002 | 250 | ✅ | ✅ | ✅ | PASS
ex_stage | FR-003 | 162 | ✅ | ✅ | ✅ | PASS
mem_stage | FR-004 | 133 | ✅ | ✅ | ✅ | PASS
wb_stage | FR-005 | 43 | ✅ | ✅ | ✅ | PASS
rv32i_core (top) | ALL | 661 | ✅ | ✅ | ✅ | PASS